## Sheet1
Task | Days |  | Status
MVP-0
100% coverage for current functional (unit testing) | 1 | 2026-03-14 | Completed
readme | 0.5
Tests desciption | 1
UI - Schema | 0.5
UI - page for watch products | 2
UI - page for create and edit products | 2
UI - manual testing | 0.5
Docker scripts | 1
CI \ CD for store | 2
Documentation | 1
MVP-1
User functional | 2
Add moderating products functional | 2
Auto verify for products functional | 1
Unit + integration tests | 2
Security - backend | 1
Tests for security | 1
UI - Schema | 0.5
UI - Login page | 1
UI - User page | 1
Add user validations for product funtional | 1
Update tests | 0.5
MVP-2
UI tests | 3
CI \ CD update | 1